## Sheet1
Leverhulme ECR Fellowship - Deadline 23rd February 2023 | Timeline | Royal Society URF - Deadline not yet annouced, likely ~5th September 2023 | Timeline | STFC Ernest Rutherford Fellowships - Deadline not yet announced, likely ~12th September 2022 | Timeline | RAEng Fellowships - Deadline not yet announced, likely ~19th September 2022 | Timeline
CoSE Launch of call | 15th November | Briefing session | 25th April | This is managed by the Schools of Physics and Astronomy and Geographical and Earth Science as they are eligible to submit applicants. | STFC state a date in August, before which, candidates cannot be confirmed. | Briefing session | 18th April
Candidate to identify supporting academic and notify scieng-submit@glasgow.ac.uk | 21st November | Candidate to identify supporting academic and notify scieng-submit@glasgow.ac.uk of intention to submit and supporting academic's name. | 15th May | Details will be issued by the schools and once candidates are selected the Research Development Team and Project Coordinators will be notified to provide the necessary support. |  | Candidate to identify supporting academic and notify scieng-submit@glasgow.ac.uk of intention to submit and supporting academic's name. | 3rd May
Submit template to supporting academic | 30th November | Submit completed template to supporting academic | 29th May | Candidates and supporting academics confirmed | ~17th August | Submit RAEng application template with statement from supporting academic to scieng-submit@glasgow.ac.uk | 24th May
Make contact with Project Coordinator for costing form and guidance | 9th December | Supporting academic reviews and submits to DoR with statement of support | 15th June | Make contact with Project Coordinator for costing form and guidance | ~17th August | RAEng review panel meets | 15th June
Supporting academic reviews and submits to DoR with statement of support | 13th December | Approval to proceed with application and to apply for LKAS from DoR | 29th June | Data Management plan required - check support available https://www.gla.ac.uk/myglasgow/datamanagement/ | ~17th August | Interviews | w/b 26th June
Approval to proceed with application and to apply for LKAS from DoR | 21st December | Make contact with Project Coordinator for costing form and guidance | 12th July | Identify nominated reviewer who will provide a letter of support, they must not be from the host institution. | 24th August | Successful applicants notified | 3rd July
Update Project Coordinator on progress | 9th January | Initial costs to Project Coordinator | 21st July | Initial costs to Project Coordinator | 25th August | Make contact with Project Coordinator for costing form and guidance | 12th July
Initial costs to Project Coordinator | 19th January | Draft application to be submitted to scieng-submit@glasgow.ac.uk | 1st August | LKAS application submitted | 25th August | Initial costs to Project Coordinator | 28th July
LKAS application submitted | 25th January | LKAS application submitted | 4th August | Draft application to be submitted to scieng-submit@glasgow.ac.uk | 31st August | Draft application to be submitted to scieng-submit@glasgow.ac.uk | 8th August
Draft application to be submitted to scieng-submit@glasgow.ac.uk | 2nd February | Draft letter of support to be sent to Research Development Manager and supporting academic for review/feedback - write it assuming LKAS has been approved. | 10th August | draft narrative CV to be submitted to scieng-submit@glasgow.ac.uk | 31st August | Peer review session | will be arranged if appropriate for candidates/ fields
Draft answers to HoS questions submitted to Research Development Manager/HoRD in Engineering | 3rd February | Letter of support to be sent to HoS (In Engineering LoS must be reviewed and approved by Head of Research Division - allow an extra week ) | 17th August | Finalise costs with PC and costing submitted to workflow | 1st September | LKAS application submitted | 11th August
Finalise costs with PC and costing submitted to workflow | 10th February | Finalise costs with PC and costing submitted to workflow | 24th August | Submit application for institutional approval minimum of 48h before funder deadline. | 8th September (actual deadline tbc) | Draft letter of support to be sent to Research Development Manager and supporting academic for review/feedback - write it assuming LKAS has been approved. | 17th August
Answers to HoS questions to be sent to HoS for approval/uploading | 10th February | Submit application for institutional approval minimum of 48h before funder deadline. | 1st September |  |  | Finalise costs with PC and costing submitted to workflow | 7th September
Submit application for institutional approval minimum 48h before funder deadline. | 21st February |  |  |  |  | Letter of support to be sent to HoS (In Engineering LoS must be approved first by Head of Research Division - allow an extra week ) | 8th September
[6 empty] | Submit application for institutional approval minimum of 48h before funder deadline. | 15th September, (actual deadline tbc)